## How To Complete
RAID Log - Risks, Actions, Issues & Decisions
The purpose of the document is to summarise the risks, issues, actions and decisions for a project in a central locations.
Track all activities in this log, and ensure that project team member have access.
It serves as a central repository where these four elements are recorded, monitored, and managed throughout the project life cycle.
By maintaining a RAID Log, a project manager can not only keep tabs on various aspects of a project but also communicate effectively with the team and stakeholders. This tool is especially useful in complex projects where multiple elements require close monitoring and management.
Continue to Risk Log >
Continue to Actions Log >
Continue to Issues Log >
Continue to Decisions Log >

## Actions Log
Ref | Task Name | Description | Owner | Status | RAG | Priority | Start Date | End Date | Actual Completion Date | Updates
1 | Requirements Gathering | Capture all functional and non-functional requirements and confirm with user representative. Obtain sign-off | Alan | Closed | OK | High | 2020-01-01 | 2023-02-15 | 2023-02-15 | Completed. You can find the results on the SharePoint drive.
2 | Design | Produce high-level solution design based on requirements | Emily | Blocked | Concern | High | 2023-02-16 | 2023-03-20 |  | Issues confirming design approach. Meeting on Monday to discuss and will share outcome.
3 | Development | Development against requirements | Sarah | Not Started |  | Medium | 2023-04-01 | 2023-05-15

## Risk Log
Risk ID | Risk Description | Risk Category | Probability | Probability Score | Impact | Impact Score | Risk Score | Mitigation Strategy | Owner | Status | Last Updated
1 | Unauthorized data access due to weak passwords | Security | High | 5 | Medium | 3 | 15 | Implement multi-factor authentication | Alan Parker | Open | 2023-02-13
2 | Budget overrun due to hardware costs | Financial | Medium | 3 | Medium | 3 | 9 | Monitor expenses weekly and adjust budget | [Owner] | Open | 2023-02-13
3 | Project delays due to vendor issues | Operational | Low | 1 | Medium | 3 | 3 | Have backup vendors in queue | [Owner] | Accepted | 2023-02-13
... | ... | ... | [5 empty] | ... | ... |  | ...

## Issues Log
Issue ID | Issue Description | Raised By | Issue Category | Severity | Assigned To | Status | Date Opened | Target Resolution Date | Actual Resolution Date | Resolution Strategy | Comments | Last Updated
1 | Some of the requirements are contradictory and need resolution | Jenny | Scope | High | Alan Parker | Closed | 2023-01-15 | 2023-01-30 | 2023-01-30 | We are to revisit the requirements with the customer |  | 2023-01-30
2 | Supplier hasn't given us a quotation on time | Mike | Financial | Low | Mike | Open | 2023-03-18 | 2023-03-23
... | ... |  | ... |  | ...

## Decisions
Decision ID | Decision Description | Decision Made By | Decision Date | Status | Category | Rationale | Comments | Last Updated
1 | Scope change: We will now include a page for historical transactions | Alan | 2023-03-12 | Open | Scope | It has been confirmed with user base that this is critical functionality. | Confirmed at meeting 22/2 with Jeff & Lindsay | 2023-03-13
2 | Overtime approval for weekend of 25/3 | Mike | 2023-02-14 | Closed | Resources | We need to implement some changes over the weekend and have agreed to do it on Saturday. |  | 2023-03-13
3 | We will be billing for the additional hours after the requirements phase. | John | 2023-02-04 | Closed | Billing | A change request (#003) has been approved by the customer |  | 2023-03-13
... | ... |  | ... |  |  |  |  | ...